## Summary
Rehabilitation Chief-of-Staff Agent — Function Update Register
Source: git history of main (304 commits / 108 PRs), README release notes, docs/v*.md · 21 Aug → 15 Sep 2026
Total updates | 122
Telegram command groups | 16
Integrations | 23
Distinct version lines | 62
By type | Count
Feature | 60
Fix | 18
Integration | 15
Enhancement | 13
Security | 6
Command | 4
Infra | 3
Docs | 2
Rollback | 1
By phase | Count
0 Foundation | 18
1 CoS Core | 23
2 Clinical | 10
3 Multi-model | 15
4 Safety & Truth | 11
5 Extensions | 6
6 Master OS | 12
7 Proactive | 17
8 Finance & Autopay | 10

## Function Updates
# | Date | Version line | Phase | Category | Type | Function / Feature | Description | Module / File | Command / CLI | PR
1 | 2026-08-21 | AI OS v0.2 | 0 Foundation | Core State | Feature | Unified StateStore | Single writer for all mutable data: atomic writes, version conflict rejection, rotating backups (last 5), audit log data/audit.jsonl. Sheet demoted to import/export. | engine/store.py
2 | 2026-08-21 | AI OS v0.2 | 0 Foundation | Governance | Feature | Action queue + approval gate (C2) | Follow-up drafts queued as PENDING_APPROVAL; approval needs SHA-256 hash of draft text; 48h expiry; idempotent. | engine/approve.py, engine/render_approvals.py | approve A-001 --hash
3 | 2026-08-21 | AI OS v0.2 | 0 Foundation | Chief of Staff | Feature | Waiting-for rot detection | Everything awaited derived into waiting_for; >14 days escalates to a decision issue. | engine/chief_of_staff.py
4 | 2026-08-21 | AI OS v0.2 | 0 Foundation | Chief of Staff | Feature | Daily brief + weekly review + pattern detection | Brief engine, weekly review, pattern detector, daily inbox HTML. | engine/chief_of_staff.py, tools/daily-inbox.html
5 | 2026-08-21 | AI OS v0.3 | 0 Foundation | Automation | Feature | Manager loop (two cycles) | Fast cycle every 15 min (waiting-for sweep) + full cycle 06:00 Riyadh (brief + dashboard), catch-up, write-on-change. | engine/manager.py | manager.py --loop
6 | 2026-08-21 | AI OS v0.3 | 0 Foundation | Core State | Enhancement | waiting_for schema v2 | WAITING→OVERDUE state machine; one idempotent follow-up per overdue item with draft. | engine/manager.py
7 | 2026-08-21 | AI OS v0.3 | 0 Foundation | Chief of Staff | Feature | decision_requests | Formal decision requests (options + deadline) for stalled projects; resolution logged with 30-day review. | engine/manager.py
8 | 2026-08-21 | AI OS v0.3 | 0 Foundation | Chief of Staff | Feature | Change detection section | 'What changed since last brief' (new / status changed / closed). | engine/chief_of_staff.py
9 | 2026-08-21 | AI OS v0.3.1 | 0 Foundation | Clinical / Voice | Feature | Inbound voice-call processor | Transcript → caller/intent classification → summary → StateStore (contacts, callbacks, leads) + follow-up draft; never sends. | engine/voice_call.py | voice_call.py demo A..E ¦ ingest
10 | 2026-08-21 | AI OS v0.3.1 | 0 Foundation | Security | Security | Voice-call hard guards | No diagnosis from calls; caller speech untrusted (injection rejected + logged); data minimisation; idempotency by call ID. | engine/voice_call.py
11 | 2026-08-21 | AI OS v0.4 | 0 Foundation | Learning | Feature | Adaptive teaching engine | Plans → graded chunks with adaptive rulings (≥85/70–84/50–69/<50) → mastery map → spaced repetition 1/3/7/14/30. | engine/learning_engine.py
12 | 2026-08-21 | AI OS v0.4 | 0 Foundation | Learning | Feature | Review lifecycle | SCHEDULED→DUE→PRESENTED→ANSWERED→SCORED→COMPLETED; brief shows max 2 reviews/day. | engine/learning_engine.py
13 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Learning | Enhancement | ILPC methodology (Bob Pike) | EAT / CPR / 90-20-8 rules; outline generator; first material LP-001 Lean Six Sigma. | prompts/personal-training.md, materials/ | learning_engine.py outline LP-001
14 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Infra | Infra | Sheet template + bootstrap + smoke test + CI | make_template, bootstrap_demo.sh, smoke_test.sh, CI workflow in docs/ci-workflow.yml. | engine/make_template.py, scripts/
15 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Integration | Integration | ChatGPT & VS Code bridge | Context export for chat + editor tasks + usage guide. | engine/export_for_chat.py, .vscode/
16 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Automation | Feature | 24/7 autostart | Windows/macOS/Linux installers + daily heartbeat. | autostart/
17 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Integration | Integration | Google Drive bridge (sheet import) | Live sheet import, decision-speed plan, fix for public-request invalidation. | engine/import_drive.py
18 | 2026-08-21 | AI OS v0.4.1 | 0 Foundation | Knowledge | Feature | Sources & scientific learning bridge | --sources mode; knowledge_sources section; import of 24 sources + 28 weak-point protocols; LP-002/LP-003. | engine/import_drive.py | --sources
19 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Life OS | Feature | 14 life doors + door of the day | Life-domain model and daily focus door in the brief; real income baseline. | engine/chief_of_staff.py | /door
20 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Knowledge | Feature | Knowledge asset registry | Unified tracking of books/docs/tabs/files/contracts; filter UI; auto-sync in full cycle. | engine/asset_registry.py
21 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Prompts | Feature | 4 new playbooks | Travel, negotiation, writing, family prompt packs. | prompts/travel.md, negotiation.md, writer.md, family.md
22 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Docs | Docs | Agent skills inventory + routing table | 11 skills + 9 engines; later audited 19/19. | docs/agent-skills.md, evaluation/skills-audit-2026-08-22.md
23 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Telegram | Feature | Full Telegram integration (v0) | Button approvals (C2), decisions, brief, capture; social triage; full-text search. | engine/telegram_bot.py, engine/social_triage.py, engine/search.py | /approve /decisions /brief
24 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Chief of Staff | Fix | Complaint pattern fix | Pattern for 'bad/complain' + cleanup of misclassified draft. | engine/chief_of_staff.py
25 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Telegram | Fix | getUpdates timeout | Timeout longer than long-poll — removes timeout noise. | engine/telegram_bot.py
26 | 2026-08-22 | AI OS v0.4.x | 1 CoS Core | Life OS | Feature | Skills wave 2: OKR, Health Guardian, finance E-S-B-I | OKR engine, energy log, real finance, green Friday brief, voice capture from Telegram. | engine/okr.py, engine/energy_log.py | /okr, energy
27 | 2026-08-22 | AI OS v0.5 | 1 CoS Core | Core | Feature | Orchestrator, permissions, memory, RAG | Core orchestration with provenance, permission model, memory, retrieval. | engine/orchestrator.py, permissions.py, memory.py, rag.py |  | #1
28 | 2026-08-22 | AI OS v0.5 | 1 CoS Core | Core | Feature | Observability, telemetry, evaluation, control center | Telemetry & observability, evaluation harness, mobile control center, v05 cycle. | engine/observability.py, telemetry.py, evaluate.py, control_center.py |  | #1
29 | 2026-08-22 | AI OS v0.5 | 1 CoS Core | Clinical / Rehab | Feature | RCJY rehabilitation leadership training | Work context, service packages, CoS scenarios; morning routing prioritises hospital leadership; PHI never in memory/GitHub. | knowledge/rcjy-*.md, training/ |  | #2
30 | 2026-08-22 | AI OS v0.6 | 1 CoS Core | Self-improvement | Feature | Self-improving learning loop | Reflection engine, behaviour model, self-review, decision quality scoring. | engine/reflection_engine.py, behavior_model.py, self_review.py, decision_quality.py |  | #3
31 | 2026-08-22 | AI OS v0.7 | 1 CoS Core | Trust | Feature | Trust, change intelligence, reliability | Change intelligence, trust dashboard, connector health, backup verification. | engine/change_intelligence.py, trust_dashboard.py, connector_health.py, backup_verify.py |  | #4
32 | 2026-08-22 | AI OS v0.8 | 1 CoS Core | Integration | Integration | Live connectors + unified source sync | Gmail, Calendar, Drive, GitHub, Telegram live connectors; unified inbox. | engine/live_sync.py, unified_inbox.py, connectors/google_workspace.py, github_live.py, telegram_live.py |  | #5
33 | 2026-08-22 | AI OS v0.9 | 1 CoS Core | Knowledge | Feature | Master professional profile + Drive governance | Profile YAML, Drive knowledge map, source policy, source governance engine. | knowledge/master-professional-profile.yaml, engine/source_governance.py |  | #6
34 | 2026-08-22 | Telegram v1 | 1 CoS Core | Telegram | Command | Secure polling bot commands | /start /help /profile /sources /selftest; owner lock via TELEGRAM_ALLOWED_CHAT_ID; security tests. | connectors/telegram_bot.py | /start /help /profile /sources /selftest
35 | 2026-08-22 | Telegram v1 | 1 CoS Core | Infra | Infra | Railway deployment | requirements.txt, Dockerfile, Bedrock dependency, Railway volume. | Dockerfile, requirements.txt
36 | 2026-08-22 | Telegram v1 | 1 CoS Core | AI Models | Integration | Claude on AWS Bedrock free-text answers | Free text answered by Claude; conversations persisted to Sheets. | connectors/telegram_bot.py | /bedrock_test
37 | 2026-08-22 | Telegram v1 | 1 CoS Core | Memory | Feature | Bounded memory + knowledge retrieval runtime | Agent runtime with memory and retrieval; Railway volume conversation state. | engine/agent_runtime.py | /context_test
38 | 2026-08-22 | Telegram v1 | 1 CoS Core | Voice | Integration | AWS Transcribe voice pipeline | Private transcription with cleanup; Telegram voice notes transcribed. | connectors/aws_transcribe.py
39 | 2026-08-22 | Telegram v1 | 1 CoS Core | Google Sheets | Integration | Apps Script secure webhook | Sheets logging/read-search/approved updates without JSON key; Sheets intelligence connector. | connectors/google_sheets_webhook.gs, sheet_intelligence.py
40 | 2026-08-22 | Telegram v1 | 1 CoS Core | AI Models | Enhancement | Profile grounding | AI responses always grounded in verified professional profile; executive tabs prioritised. | evaluation/profile-grounding-cases.json
41 | 2026-08-22 | Telegram v1 | 1 CoS Core | Telegram | Fix | Repair Sheets commands + syntax validation | Fixed Telegram Sheets commands, validated Python syntax. | connectors/telegram_bot.py
42 | 2026-08-24 | Rehab v1.3 | 2 Clinical | Clinical / Rehab | Feature | Executive brief discovery | /brief reads bounded Sheets snapshot, diffs vs last, detects changes/blockers/decisions; updates Executive_Brief tab. | connectors/brief_discovery.py | /brief | #8
43 | 2026-08-24 | Rehab v1.3 | 2 Clinical | Clinical / Rehab | Integration | Rehab supervisor Google Form | createRehabSupervisorForm + testRehabIntegration. | connectors/rehab_supervisor_form.gs |  | #8
44 | 2026-08-24 | Phase 1.5 | 2 Clinical | Clinical / Rehab | Feature | Safe pre-visit intelligence | Case-code only; safety screen first; URGENT/PRIORITY/ROUTINE review labels; irritability; gaps; hypotheses for clinician review only. | engine/previsit_intelligence.py, prompts/previsit-intelligence.md, connectors/previsit_patient_form.gs |  | #9
45 | 2026-08-24 | Phase 1.5 | 2 Clinical | Clinical / Rehab | Feature | Approved pre-visit link workflow | Pre-visit links issued only through approval. | engine/previsit_intelligence.py |  | #9
46 | 2026-08-24 | Rehab v1.3 | 2 Clinical | Telegram | Fix | Brief availability + Telegram formatting | Brief kept available before gateway upgrade; readable formatting. | connectors/brief_discovery.py
47 | 2026-08-24 | P0 | 2 Clinical | Telegram | Security | Switch to webhook + harden Sheets/privacy | Polling → webhook; privacy hardening. | connectors/telegram_webhook.py |  | #10
48 | 2026-08-24 | P0 | 2 Clinical | Telegram | Fix | Duplicated /brief + Sheets timeout | Fixed duplicate brief and timeout path. | connectors/telegram_webhook.py |  | #11
49 | 2026-08-25 | Memory | 2 Clinical | Memory | Fix | Historical memory retrieval + save receipts | Verified save receipts. | engine/context_service.py | /memory_status
50 | 2026-08-25 | Memory | 2 Clinical | Memory | Feature | Provenance-first semantic context retrieval | Unified multi-source retrieval; durable provenance-aware memory; Arabic prefixes; contract concept expansion. | engine/context_service.py | /memory /confirm_memory /update_memory
51 | 2026-08-25 | Calendar | 2 Clinical | Google Calendar | Feature | Confirmed Calendar actions + reminder scheduler | Create/confirm events, Telegram reminders, Arabic dual-hour phrasing, service-account access, consent docs. | connectors/calendar_actions.py, calendar_intent.py
52 | 2026-08-27 | Prod v0.5a | 3 Multi-model | AI Models | Integration | OpenRouter primary + Bedrock fallback | Model gateway with permanent Bedrock fallback; model-router CI. | connectors/model_gateway.py |  | #14
53 | 2026-08-28 | Prod v0.6 | 3 Multi-model | AI Models | Feature | Multi-agent task delegation | Delegate agents + council; routing and privacy guard tests. | connectors/task_delegation.py | /delegate /agents /council | #15
54 | 2026-08-28 | Prod v0.7 | 3 Multi-model | Google | Integration | Read-only Google knowledge gateway | Knowledge read commands + diagnostics; allowlist & URL parsing tests. | (rolled back) | /google_access | #16
55 | 2026-08-28 | Prod v0.7.1 | 3 Multi-model | Google | Fix | Robust service-account parsing | Hotfix. | (rolled back) |  | #17
56 | 2026-08-28 | Prod v0.8 | 3 Multi-model | Google | Integration | Apps Script knowledge gateway (Sheets + Drive) | Preferred in production; diagnostics in /google_access. | (rolled back) | /google_access | #18-#20
57 | 2026-08-28 | Prod v0.8.1 | 3 Multi-model | Google | Rollback | Rollback Google Knowledge | Restored stable v0.6 workflow (8 rollback commits). | connectors/ |  | #21
58 | 2026-08-28 | Mission v0.7 | 3 Multi-model | AI Models | Feature | AI Team Mission Orchestrator | Shared missions for Claude, GPT, Gemini; specialists via direct APIs; Gemini fallback hotfix; provider diagnostics. | connectors/team_orchestrator.py, direct_specialists.py, provider_diagnostics.py | /mission | #22-#26
59 | 2026-08-28 | Mission v0.8 | 3 Multi-model | AI Models | Enhancement | Sequential Gemini→GPT handoff | Ordered specialist handoff. | connectors/team_orchestrator.py |  | #27
60 | 2026-08-28 | Mission v0.9 | 3 Multi-model | AI Models | Feature | Bedrock-first lean token budgets | Lightweight Bedrock team adapter; token-budgeted missions; de-identified guardrail; research capsule format. | connectors/bedrock_team.py, lean_missions.py |  | #28
61 | 2026-08-28 | Mission v0.9.1 | 3 Multi-model | AI Models | Enhancement | Bedrock diagnostics + tiny probe | Probe command for Bedrock team models. | connectors/bedrock_team.py |  | #29
62 | 2026-08-28 | Mission v0.9.2 | 3 Multi-model | AI Models | Enhancement | Nova Micro default lean model | Cheaper default for lean missions. | connectors/lean_missions.py |  | #30
63 | 2026-08-28 | Prod v0.9.3 | 3 Multi-model | Context | Feature | On-demand operational context capsules | Ops context + source status (v0.9.3a). | connectors/ops_context.py |  | #31-#32
64 | 2026-08-28 | Prod v0.9.4 | 3 Multi-model | Google | Enhancement | Hardened Google context transport | Mounted credential files; runtime failure reasons (v0.9.4a). | connectors/google_credentials.py |  | #34-#36
65 | 2026-08-28 | Prod v0.9.5 | 3 Multi-model | Google Calendar | Fix | Calendar reminders in webhook mode | Reminder worker kept alive under webhook. | connectors/telegram_webhook_runtime.py |  | #37
66 | 2026-08-28 | Prod v0.9.6 | 3 Multi-model | Google Calendar | Feature | NL Calendar requests → guarded actions | Natural-language routing + mobile-friendly confirmation. | connectors/mobile_calendar_confirm.py |  | #38-#39
67 | 2026-08-29 | Portfolio v1 | 4 Safety & Truth | Portfolio | Feature | Portfolio page | Rehab & healthcare-AI expert page; LinkedIn; GitHub Pages; CV 2026 V3 refresh; later archived. | portfolio/ |  | #40-#42
68 | 2026-08-29 | Sheets | 4 Safety & Truth | Google Sheets | Fix | Direct-first Sheets writes + import path | Direct route, diagnostics, resilient writes. | connectors/google_sheets_* |  | #43-#45
69 | 2026-08-29 | Direct Brief v2 | 4 Safety & Truth | Clinical / Rehab | Enhancement | Direct Brief v2 → v2.1 | Rebuilt /brief as direct Sheets runtime command; v2.1 adds Google Calendar. | connectors/brief_runtime.py | /brief | #46-#49
70 | 2026-08-29 | Gate 0.5 | 4 Safety & Truth | Security | Security | Fail closed on ambiguous Calendar dates/times | Regression tests for ambiguity; invalid references (30 Aug). | connectors/calendar_intent.py |  | #63
71 | 2026-08-30 | State Safety | 4 Safety & Truth | Core State | Enhancement | StateStore concurrency + persistent markers | Transactional Manager writes, loop markers, CI tests. | engine/store.py, engine/manager.py |  | #64
72 | 2026-08-30 | WO-8 | 4 Safety & Truth | Inbox | Feature | Linked multi-intent capture | Conservative multi-intent recorder; multi-intent-aware unified inbox. | engine/multi_intent.py, connectors/multi_intent_runtime.py |  | #65
73 | 2026-08-30 | Super Manager v1.1 | 4 Safety & Truth | Chief of Staff | Feature | Super Manager | Grounded in WO-8 record links; FAST compat with NEEDS_INPUT. | connectors/super_manager.py | /manager /manager_status | #66
74 | 2026-08-30 | Canary | 4 Safety & Truth | Automation | Feature | FAST-only Manager canary (flag OFF) | Wired into webhook runtime behind disabled flag. | connectors/manager_fast_canary.py | /manager_shadow | #67
75 | 2026-08-31 | Capability Truth | 4 Safety & Truth | Governance | Feature | Capability Truth + action preflight | Runtime truth about tools; privacy correction; blocks blanket text-only denial; shopping boundaries. | connectors/capability_truth.py, capability_runtime.py | /capabilities | #68
76 | 2026-08-31 | NL Actions | 4 Safety & Truth | Actions | Feature | Natural-language Action Executor | Approval receipts; deadline/reminder/project report; reminder negation; language safety. | connectors/action_executor.py, action_runtime.py, action_deadline_report.py, action_language_safety.py | /act /action_status /approve_action /reject_action | #69
77 | 2026-08-31 | Exec Brief v3 | 4 Safety & Truth | Clinical / Rehab | Enhancement | Executive signal discovery | Constraints, logistics, commitments, status; StateStore route; 06:45 travel rule; departure calculation. | connectors/executive_signals.py, brief_signal_runtime.py | /brief | #70
78 | 2026-09-01 | Capability Truth v2 | 5 Extensions | Governance | Enhancement | Ground read-only Main Sheet requests | Regressions for read-only sheet capability. | connectors/capability_truth.py |  | #71
79 | 2026-09-01 | Commerce | 5 Extensions | Commerce | Feature | Commerce Agent core | Trusted checkout adapter, read-only deal scout, sandbox smoke test, Telegram runtime. | connectors/commerce_agent.py, commerce_checkout.py, commerce_scout.py, commerce_sandbox.py, commerce_runtime.py | /shop /prepare_order /approve_order /commerce_status /commerce_test | #73
80 | 2026-09-01 | Commerce | 5 Extensions | Security | Security | $100 pilot order + daily caps | Defense-in-depth cap. | connectors/commerce_agent.py |  | #73
81 | 2026-09-02 | Bridge | 5 Extensions | API | Feature | First-party /chat Bridge API | BRIDGE_API_KEY-protected POST /chat; unified ask alias. | connectors/bridge_api.py | POST /chat
82 | 2026-09-03 | CI | 5 Extensions | Infra | Infra | Strategic shadow DEV runner | Manual isolated runner; safe prerequisite reporting; bounded concurrency. | .github/workflows/strategic-shadow-dev.yml
83 | 2026-09-04 | Books v3.0 | 5 Extensions | Knowledge | Feature | Books context (learning shelf) | Book retrieval, Super Manager integration, fast path in Telegram; v2.0 → v3.0. | engine/books_context.py | /books
84 | 2026-09-08 | Connectors | 6 Master OS | Google Docs | Integration | Google Docs connector + connection doctor | Unified connection status checker; docs & tab creation from the bot. | connectors/google_docs_service.py, connection_setup.py |  | #78
85 | 2026-09-08 | Connectors | 6 Master OS | Docs | Docs | Interactive connection walkthrough page | Checkboxes, print/PDF, offline; Buffer setup phase. | docs/connection-walkthrough.html |  | #78
86 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Knowledge | Feature | Google Drive standard tree + drive_tree | Abdulrahman_Master_OS roots 01–05; render/checklist. | engine/master_os.py, drive_tree.py | drive_tree.py render¦checklist | #80
87 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Agents | Feature | Four sub-agents matrix | Morning Briefing / Clinical & Ops / Knowledge & Audio / Finance & Life. | prompts/master-os-agents.md |  | #80
88 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Automation | Feature | Automation scheduler (11 jobs, Riyadh) | Daily 06:45/07:30/16:00/20:30; weekly Sun/Tue/Thu/Fri; monthly 28/1/last; drafts only. | engine/scheduler.py | /schedule, scheduler.py today-actions | #80
89 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Knowledge | Feature | Mind-map generator | Markdown → Mermaid mindmap + text tree + library; Friday map. | engine/mindmap.py | /mind_maps | #80
90 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Voice | Feature | Audio digest pipeline | QUEUED→DIGESTED→NARRATED; 5–7 min script; mp3 via ElevenLabs. | engine/audio_digest.py | /audio_digests | #80
91 | 2026-09-09 | AI OS v0.9 Master OS | 6 Master OS | Telegram | Command | Master OS panel commands | /masteros /schedule /mind_maps /audio_digests /today_actions /run | engine/telegram_bot.py | /masteros /run /today_actions | #80
92 | 2026-09-09 | v0.9 live wiring | 6 Master OS | Voice | Integration | ElevenLabs voice channel | Config + live probe in connection setup. | connectors/connection_setup.py |  | #81
93 | 2026-09-09 | v0.9 live wiring | 6 Master OS | Telegram | Command | /diag channel status | Presence-only offline diagnostics; empty-state hardening. | engine/telegram_bot.py | /diag | #81
94 | 2026-09-09 | v0.9 live wiring | 6 Master OS | Telegram | Fix | Wire Master OS commands to production runtime | Commands & callbacks in webhook runtime. | connectors/telegram_webhook_runtime.py |  | #82
95 | 2026-09-09 | v0.9 live wiring | 6 Master OS | Telegram | Fix | Reply noise removed | No routine footers; task-first brevity policy. | connectors/telegram_webhook_runtime.py |  | #83
96 | 2026-09-11 | Proactive v1.0 | 7 Proactive | Proactive | Feature | Proactive Chief of Staff loop | observe→remember→predict→score→decide→act/prepare/alert→learn in one Store transaction; from manager --loop. | engine/proactive.py | proactive.py sweep¦brief¦status¦orders | #85
97 | 2026-09-11 | Proactive v1.0 | 7 Proactive | Proactive | Feature | Open loops register | Commitments to self/from others, renewals, decisions, project risks. | engine/proactive.py |  | #85
98 | 2026-09-11 | Proactive v1.0 | 7 Proactive | Governance | Feature | Autonomy ladder L0–L4 per category | Comms/money/legal/health/reputation L0–L1; internal tasks L2–L3; no global free-act switch. | engine/proactive.py |  | #85
99 | 2026-09-11 | Proactive v1.0 | 7 Proactive | Proactive | Feature | 8 standing orders | Meeting prep, appointment window, rotting waits, money due, renewals, conflicts, travel, missed-commitment recovery. | engine/proactive.py | order-disable SO-00x | #85
100 | 2026-09-11 | Proactive v1.0 | 7 Proactive | Governance | Security | Proactive guards | Confidence<0.8 prepare only; 6 alerts/day; quiet hours 22:00–06:30; undo; pause; audit. | engine/proactive.py | undo PA-xxxx, pause --hours 4, feedback | #85
101 | 2026-09-11 | Proactive v1.0.1 | 7 Proactive | Telegram | Integration | Urgent-alert Telegram channel | proactive_alert push + first live sweep. | engine/proactive.py | proactive.py push-test | #85
102 | 2026-09-11 | Proactive v1.0.2 | 7 Proactive | Telegram | Command | Proactive bot commands | /proactive /sweep /proactive_test | connectors/telegram_webhook_runtime.py | /proactive /sweep /proactive_test | #85
103 | 2026-09-11 | Proactive v1.0.3 | 7 Proactive | Self-improvement | Feature | Weekly acceptance review + bounded self-tuning | Adjusts confidence threshold / max alerts; guard ≥5 decisions. | engine/proactive.py | proactive.py review --apply | #85
104 | 2026-09-11 | Buffer | 7 Proactive | Publishing | Integration | Buffer publisher | GraphQL connector, setup guide, status check, --service resolution, GitHub Action, PR post queue. | connectors/buffer_publisher.py, .github/workflows/buffer-publish.yml, posts/buffer/ |  | #90-#91
105 | 2026-09-11 | Content | 7 Proactive | Automation | Feature | Production proactive worker | Runs in webhook every 15 min; last_proactive_worker marker. | connectors/proactive_worker.py |  | #95
106 | 2026-09-11 | Content | 7 Proactive | Publishing | Feature | Content Creator orchestra | Researcher → critic → creator; preview; approve/reject; status. | connectors/content_creator.py, content_runtime.py | /content /approve_content /reject_content /content_status | #95
107 | 2026-09-11 | Content | 7 Proactive | Google Sheets | Integration | Life Pulse publishing sheet | Reads Ready/Idea rows; writes PUBLISH_QUEUE. | connectors/content_sheet.py | /content_sheet /content_sheet_status | #96
108 | 2026-09-11 | Content | 7 Proactive | Publishing | Fix | Low OpenRouter credit resilience | Workflow continues on low credit. | connectors/content_creator.py |  | #97
109 | 2026-09-11 | Content | 7 Proactive | Publishing | Fix | Truncated Content Creator JSON recovery | Safe recovery. | connectors/content_creator.py |  | #98
110 | 2026-09-11 | Content | 7 Proactive | Governance | Enhancement | Runtime-truth grounding for publishing/proactive answers | No invented status. | connectors/capability_truth.py |  | #99
111 | 2026-09-12 | Content | 7 Proactive | Publishing | Feature | Gemini image & video workflow | Design/video content commands; Sheet queue IDs accepted. | connectors/content_media.py | /design_content /video_content /media_status | #100-#101
112 | 2026-09-12 | Books | 7 Proactive | Knowledge | Fix | Learning-tab name variants | Tolerate variants; stop silent fall-through. | engine/books_context.py |  | #102
113 | 2026-09-14 | Prod fix | 8 Finance & Autopay | Automation | Fix | Dispatch scheduler from production worker | Due scheduler jobs run from webhook worker. | connectors/proactive_worker.py |  | #103
114 | 2026-09-14 | Prod fix | 8 Finance & Autopay | Memory | Fix | Scheduler persistence + Drive project memory | Riyadh scheduler persisted; Google Drive project memory connector. | connectors/project_memory.py |  | #104
115 | 2026-09-14 | Prod fix | 8 Finance & Autopay | Runtime | Fix | Real-clock anchor + /time probe | Stopped crash-loop; agent anchored to real clock. | engine/runtime_clock.py | /time | #105
116 | 2026-09-15 | AI OS v2.0 | 8 Finance & Autopay | Finance | Feature | Unified Finance Hub v2.0 | finance as single truth; webhook/CSV/manual pull; monthly snapshot with health_index; Thu 07:00 + 1st 07:30 + hourly. | engine/finance_hub.py | system_status.py --finance | #106
117 | 2026-09-15 | AI OS v2.0 | 8 Finance & Autopay | Automation | Enhancement | Dormant layers activated (14/14) | asset_registry, backup_verify, change_intelligence, observability, trust_dashboard in manager loop. | engine/manager.py | system_status.py --layers --schedule | #106
118 | 2026-09-15 | AI OS v2.0 | 8 Finance & Autopay | Proactive | Fix | Proactive live context | No more INFERENCE/MISSING for finance/proactive in bot. | engine/system_status.py |  | #106
119 | 2026-09-15 | Web search | 8 Finance & Autopay | Search | Feature | Verified YouTube search | Only verified watch?v= links; auto-attach; DuckDuckGo default, optional YouTube API; PII stripped. | connectors/web_search.py | /youtube /search | #107
120 | 2026-09-15 | Money v1.1 | 8 Finance & Autopay | Finance | Feature | Money threshold autopay < 375 SAR | money L1→L3 under threshold via payment gateway with receipt/undo; ≥375 or unknown stays red draft. | connectors/payment_gateway.py, engine/proactive.py | proactive.py threshold¦matrix¦status | #108
121 | 2026-09-15 | Money v1.1 | 8 Finance & Autopay | Security | Security | Autopay guards | ENABLED flag + ACK phrase + gateway + known amount + daily cap 375 + idempotency; HARD_MAX_SAR in code; env can only lower. | connectors/payment_gateway.py |  | #108
122 | 2026-09-15 | Money v1.1 | 8 Finance & Autopay | Core State | Feature | autopay_executions ledger + audit events | autopay_authorized/executed/failed/blocked; sandbox connector; 18 tests; verify script. | connectors/payment_sandbox.py, tests/test_money_threshold.py, scripts/verify_money_threshold.sh | bash scripts/verify_money_threshold.sh | #108

## Telegram Commands
Introduced | Commands | Purpose
2026-08-22 | /start /help /profile /sources /selftest | Bot basics, profile, source counts, self-test
2026-08-22 | /okr /tasks /decisions /approve /door /mastery /reviews /answer | OKR, tasks, decisions, approvals, life door, learning reviews
2026-08-22 | /manager /manager_status /bedrock_test /context_test | Manager loop status, model & context probes
2026-08-24 | /brief | Executive brief discovery (v1.3 → Direct Brief v2.1 → Exec Brief v3)
2026-08-25 | /memory /memory_status /confirm_memory /update_memory /storage_status | Provenance memory management
2026-08-28 | /delegate /agents /council /mission /google_access | Multi-agent delegation & missions
2026-08-30 | /manager_shadow | FAST manager canary (flag OFF)
2026-08-31 | /capabilities /act /action_status /approve_action /reject_action | Capability truth & natural-language actions
2026-09-01 | /shop /prepare_order /approve_order /commerce_status /commerce_test | Commerce agent ($100 pilot caps)
2026-09-04 | /books | Learning shelf book retrieval
2026-09-09 | /masteros /schedule /mind_maps /mindmaps /digests /audio_digests /today_actions /run /diag | Master OS panel & diagnostics
2026-09-11 | /proactive /sweep /proactive_test | Proactive Chief of Staff
2026-09-11 | /content /approve_content /reject_content /content_status /content_sheet /content_sheet_status | Content Creator & publishing sheet
2026-09-12 | /design_content /video_content /media_status | Gemini image/video content
2026-09-14 | /time | Real-clock liveness probe
2026-09-15 | /youtube /search | Verified YouTube search

## Integrations
Introduced | Integration | Module | Status
2026-08-21 | Google Drive (sheet import) | engine/import_drive.py | Active
2026-08-21 | ChatGPT / VS Code bridge | engine/export_for_chat.py | Active
2026-08-22 | Telegram (polling) | connectors/telegram_bot.py | Superseded by webhook 24 Aug
2026-08-22 | AWS Bedrock (Claude) | connectors/telegram_bot.py | Active (fallback)
2026-08-22 | AWS Transcribe | connectors/aws_transcribe.py | Active
2026-08-22 | Google Sheets — Apps Script webhook | connectors/google_sheets_webhook.gs | Active
2026-08-22 | Gmail / Calendar / Drive / GitHub live connectors | connectors/google_workspace.py, github_live.py | Active
2026-08-22 | Railway (container + volume) | Dockerfile | Active
2026-08-24 | Telegram (webhook) | connectors/telegram_webhook.py | Active
2026-08-24 | Google Forms (supervisor, pre-visit) | connectors/*.gs | Active
2026-08-25 | Google Calendar actions | connectors/calendar_actions.py | Active
2026-08-27 | OpenRouter | connectors/model_gateway.py | Active (primary)
2026-08-28 | OpenAI GPT & Google Gemini (direct) | connectors/direct_specialists.py | Active
2026-08-28 | Bedrock Nova Micro (lean) | connectors/bedrock_team.py | Active
2026-08-28 | Google Knowledge gateway | — | Rolled back (#21)
2026-09-02 | Bridge API /chat | connectors/bridge_api.py | Active
2026-09-08 | Google Docs | connectors/google_docs_service.py | Active
2026-09-09 | ElevenLabs | connectors/connection_setup.py, engine/audio_digest.py | Active (key in env)
2026-09-11 | Buffer (GraphQL) | connectors/buffer_publisher.py | Active
2026-09-12 | Gemini image/video | connectors/content_media.py | Active
2026-09-14 | Google Drive project memory | connectors/project_memory.py | Active
2026-09-15 | YouTube Data API / DuckDuckGo | connectors/web_search.py | Active
2026-09-15 | Payment gateway webhook (+sandbox) | connectors/payment_gateway.py | Active, opt-in guarded

## Growth Metrics
Date | Engine modules | Connectors | Test files | Prompt packs | Docs | Commits/day
2026-08-21 | 13 | 0 | 0 | 7 | 3 | 14
2026-08-22 | 51 | 8 | 1 | 13 | 12 | 40
2026-08-24 | 52 | 13 | 3 | 14 | 13 | 7
2026-08-25 | 53 | 14 | 5 | 14 | 13 | 14
2026-08-27 | 53 | 16 | 6 | 14 | 13 | 1
2026-08-28 | 53 | 26 | 16 | 14 | 13 | 68
2026-08-29 | 53 | 27 | 16 | 14 | 13 | 20
2026-08-30 | 54 | 30 | 21 | 14 | 14 | 30
2026-08-31 | 54 | 38 | 24 | 14 | 14 | 22
2026-09-01 | 54 | 43 | 25 | 14 | 14 | 13
2026-09-02 | 54 | 44 | 25 | 14 | 14 | 3
2026-09-03 | 54 | 44 | 25 | 14 | 14 | 6
2026-09-04 | 55 | 44 | 25 | 14 | 14 | 6
2026-09-08 | 55 | 46 | 28 | 14 | 16 | 4
2026-09-09 | 60 | 46 | 33 | 15 | 18 | 8
2026-09-11 | 61 | 51 | 37 | 16 | 20 | 13
2026-09-12 | 61 | 52 | 39 | 16 | 20 | 3
2026-09-14 | 62 | 54 | 42 | 16 | 21 | 3
2026-09-15 | 64 | 57 | 44 | 16 | 29 | 5

## Version Lines
Version line | First | Last | Updates
AI OS v0.2 | 2026-08-21 | 2026-08-21 | 4
AI OS v0.3 | 2026-08-21 | 2026-08-21 | 4
AI OS v0.3.1 | 2026-08-21 | 2026-08-21 | 2
AI OS v0.4 | 2026-08-21 | 2026-08-21 | 2
AI OS v0.4.1 | 2026-08-21 | 2026-08-21 | 6
AI OS v0.4.x | 2026-08-22 | 2026-08-22 | 8
AI OS v0.5 | 2026-08-22 | 2026-08-22 | 3
AI OS v0.6 | 2026-08-22 | 2026-08-22 | 1
AI OS v0.7 | 2026-08-22 | 2026-08-22 | 1
AI OS v0.8 | 2026-08-22 | 2026-08-22 | 1
AI OS v0.9 | 2026-08-22 | 2026-08-22 | 1
Telegram v1 | 2026-08-22 | 2026-08-22 | 8
Rehab v1.3 | 2026-08-24 | 2026-08-24 | 3
Phase 1.5 | 2026-08-24 | 2026-08-24 | 2
P0 | 2026-08-24 | 2026-08-24 | 2
Memory | 2026-08-25 | 2026-08-25 | 2
Calendar | 2026-08-25 | 2026-08-25 | 1
Prod v0.5a | 2026-08-27 | 2026-08-27 | 1
Prod v0.6 | 2026-08-28 | 2026-08-28 | 1
Prod v0.7 | 2026-08-28 | 2026-08-28 | 1
Prod v0.7.1 | 2026-08-28 | 2026-08-28 | 1
Prod v0.8 | 2026-08-28 | 2026-08-28 | 1
Prod v0.8.1 | 2026-08-28 | 2026-08-28 | 1
Mission v0.7 | 2026-08-28 | 2026-08-28 | 1
Mission v0.8 | 2026-08-28 | 2026-08-28 | 1
Mission v0.9 | 2026-08-28 | 2026-08-28 | 1
Mission v0.9.1 | 2026-08-28 | 2026-08-28 | 1
Mission v0.9.2 | 2026-08-28 | 2026-08-28 | 1
Prod v0.9.3 | 2026-08-28 | 2026-08-28 | 1
Prod v0.9.4 | 2026-08-28 | 2026-08-28 | 1
Prod v0.9.5 | 2026-08-28 | 2026-08-28 | 1
Prod v0.9.6 | 2026-08-28 | 2026-08-28 | 1
Portfolio v1 | 2026-08-29 | 2026-08-29 | 1
Sheets | 2026-08-29 | 2026-08-29 | 1
Direct Brief v2 | 2026-08-29 | 2026-08-29 | 1
Gate 0.5 | 2026-08-29 | 2026-08-29 | 1
State Safety | 2026-08-30 | 2026-08-30 | 1
WO-8 | 2026-08-30 | 2026-08-30 | 1
Super Manager v1.1 | 2026-08-30 | 2026-08-30 | 1
Canary | 2026-08-30 | 2026-08-30 | 1
Capability Truth | 2026-08-31 | 2026-08-31 | 1
NL Actions | 2026-08-31 | 2026-08-31 | 1
Exec Brief v3 | 2026-08-31 | 2026-08-31 | 1
Capability Truth v2 | 2026-09-01 | 2026-09-01 | 1
Commerce | 2026-09-01 | 2026-09-01 | 2
Bridge | 2026-09-02 | 2026-09-02 | 1
CI | 2026-09-03 | 2026-09-03 | 1
Books v3.0 | 2026-09-04 | 2026-09-04 | 1
Connectors | 2026-09-08 | 2026-09-08 | 2
AI OS v0.9 Master OS | 2026-09-09 | 2026-09-09 | 6
v0.9 live wiring | 2026-09-09 | 2026-09-09 | 4
Proactive v1.0 | 2026-09-11 | 2026-09-11 | 5
Proactive v1.0.1 | 2026-09-11 | 2026-09-11 | 1
Proactive v1.0.2 | 2026-09-11 | 2026-09-11 | 1
Proactive v1.0.3 | 2026-09-11 | 2026-09-11 | 1
Buffer | 2026-09-11 | 2026-09-11 | 1
Content | 2026-09-11 | 2026-09-12 | 7
Books | 2026-09-12 | 2026-09-12 | 1
Prod fix | 2026-09-14 | 2026-09-14 | 3
AI OS v2.0 | 2026-09-15 | 2026-09-15 | 3
Web search | 2026-09-15 | 2026-09-15 | 1
Money v1.1 | 2026-09-15 | 2026-09-15 | 3